## Unit#1
Milestones | Contractual | Actual/ Anticipated
Notice to Proceed | 2019-06-21
Supply of Foundation Bolts | 2020-02-21 | 2020-03-20
Start of Boiler Erection | 2021-02-23 | 2020-10-21
Ceiling Girder Final Jack up | 2022-01-06 | 2022-02-02
Boiler Hydro test | 2023-01-08 | 2023-06-16
Boiler Light Up | 2023-07-10 | 2025-01-17
Synchronisation | 2023-11-10 | 2025-05-28
Trial Operation Completion | 2024-02-07
Completion of all facilities | 2024-03-09

## Unit#2
Milestones | Contractual | Actual/ Anticipated
Notice to Proceed | 2019-06-21
Supply of Foundation Bolts | 2020-12-24 | 2020-11-09
Start of Boiler Erection | 2021-09-09 | 2021-11-23
Ceiling Girder Final Jack up | 2022-05-08 | 2022-12-01
Boiler Hydro test | 2023-05-10 | 2025-01-03
Boiler Light Up | 2023-11-10 | 2025-08-25
Synchronisation | 2024-03-09 | 2025-11-26
Trial Operation Completion | 2024-06-09
Completion of all facilities | 2024-07-09